## Sheet1
Category | Label | Value
Bug ID | ID # | 0
| Name | Notification Error
| Reporter | Lee Kelvin
| Submit Date | 2017-11-02
Bug Overview | Summary | “Skill Used” Notification pops while attempting to end turn
| Status | Repaired as of 11/15/2017
Environment | Platform | Windows
| OS | Windows 10
Bug Detail | Steps to reproduce | Click "end turn" button during your turn
| Expected Result | The button silently executes
| Actual Result | A "skill use" notification appears
| Description | /
Bug Tracking | Severity | Low
| Assigned to | Qiangxiang Ma
| Priority | Low
Category | Label | Value
Bug ID | ID # | 1
| Name | Skill Activation
| Reporter | Qiangxiang Ma
| Submit Date | 2017-11-02
Bug Overview | Summary | A per-turn-once skill was activated twice in same turn
| Status | Repaired as of 11/15/2017
Environment | Platform | Windows
| OS | Windows 10
Bug Detail | Steps to reproduce | Activate an used skill another time
| Expected Result | Error notification "skill used" pops up and activation is denied
| Actual Result | A "skill use" notification appears
| Description | /
Bug Tracking | Severity | High
| Assigned to | Qiangxiang Ma
| Priority | High
Category | Label | Value
Bug ID | ID # | 2
| Name | Card Status
| Reporter | Lee Kelvin
| Submit Date | 2017-11-02
Bug Overview | Summary | Card status evaluation failed to free a card slot
| Status | Repaired as of 11/15/2017
Environment | Platform | Windows
| OS | Windows 10
Bug Detail | Steps to reproduce | Kill a building card that is not finished
| Expected Result | The card slot will display "empty" and new cards can be placed inside
| Actual Result | "This card is inactive" appears when try to place card in that slot
| Description | /
Bug Tracking | Severity | Medium
| Assigned to | Qiangxiang Ma
| Priority | Medium
Category | Label | Value
Bug ID | ID # | 3
| Name | Player Stats Calculation Error
| Reporter | Lee Kelvin
| Submit Date | 2017-11-04
Bug Overview | Summary | VP and SP was incorrectly calculated after a building card is destroyed
| Status | Repaired as of 11/20/2017
Environment | Platform | Windows
| OS | Windows 10
Bug Detail | Steps to reproduce | Kill a building the other player owns
| Expected Result | SP and VP don't change as a result
| Actual Result | SP and VP incorrectly reduces
| Description | /
Bug Tracking | Severity | High
| Assigned to | Qiangxiang Ma
| Priority | High
Category | Label | Value
Bug ID | ID # | 4
| Name | Skill Activation
| Reporter | Lee Kelvin
| Submit Date | 2017-11-02
Bug Overview | Summary | Monster 206 summoned will not correctly update itself at the beginning and ending of each turn
| Status | Repaired as of 11/20/2017
Environment | Platform | Windows
| OS | Windows 10
Bug Detail | Steps to reproduce | Summon Monster 206 with building "Summoning Circle"
| Expected Result | Monster 206 will update its status at the beginning and ending of each turn
| Actual Result | No update was occuring
| Description | /
Bug Tracking | Severity | Medium
| Assigned to | Qiangxiang Ma
| Priority | High
Category | Label | Value
Bug ID | ID # | 1
| Name | Game Initialization - Quick Match
| Reporter | Lee Kelvin
| Submit Date | 2017-12-06
Bug Overview | Summary | In quick match mode, combat window will be produced twice
| Status | Repaired as of 12/6/2017
Environment | Platform | Windows
| OS | Windows 10
Bug Detail | Steps to reproduce | Accept a duel in quick match
| Expected Result | One game window
| Actual Result | Two game windows
| Description | /
Bug Tracking | Severity | High
| Assigned to | Qiangxiang Ma
| Priority | High