## Sheet1
shili wu
| Description | Week | Duration
| Code Orientation | 1 | 1
| Beginner Guide Flow Construction | 2 | 1
| Beginner Guide GUI Layout | 3 | 2
| Beginner Guide Functionality Implementation | 5 | 3
| Beginner guide Testing and Debugging | 8 | 1
| Beginnger Guide Integration into the whole system | 9 | 1
| Finalizing report, and system level debugging | 10 | 1
| Description | Week | Duration
qiangxiang ma | Coop GUI design and creation | 1 | 1
| Coop GUI functionality Implementation | 2 | 2
| Coop GUI functionality debugging | 3 | 1
| AI structure design and core functionality implementation | 4 | 1
| AI operational(make the AI able to play game) | 5 | 1
| basic AI testing | 6 | 1
| AI improvement | 6 | 2
| Advanced AI testing | 8 | 1
| Whole System testing and debugging | 9 | 1
| Finalizing Repory, debugging | 10 | 1
| Description | Week | Duration
Lee Kelvin | Acount, card, friendlist database | 1 | 1
| Encryption System, Registration Webpage | 2 | 1
| Web Version Layout Implementation | 3 | 1
| Web Version Functionality Implementation | 4 | 2
| Web Version Debugging | 5 | 1
| Level System implementation | 6 | 2
| Level System debugging | 8 | 1
| Whole System Testing and debugging | 9 | 1
| Finalize report and debug | 10 | 1
| Description | Week | Duration
Yuhao Bai | Web Version GUI Layout | 1 | 2
| Web Version Server construction | 3 | 1
| Match Finding Implementation and debugging | 4 | 2
| Game Mechanic Implementation | 5 | 4
| Web Version Debugging | 9 | 1
| Finalize report and debug | 10 | 1